## Improved Dynamic Study Plan
Chapter / Unit | Description | Hours | Complete by | Week | Due | Done |  | Avg Hours Per Week (ALL): | 11.3249 | Start Date: | 2018-01-02 | Target months to complete: | 4.27
1 | Getting started with Intermediate Data Science: Python | 0.083333 | 2018-01-02 | 1 |  | X |  | Avg Hours Per Day (ALL) | 1.6178 | Target End Date: | 2018-05-09
2.1 | Demystifying Data Science | 0.66667 | 2018-01-02 09:53 | 1 |  | X
2.2 | Start Thinking About Your Capstone Project | 1.5 | 2018-01-03 08:08 | 1 |  | X |  | Avg Hours Per Week (REMAIN) | 16.5035 | Avg Hours Per Week (CERT) | 10.8419
3.1.1 | Set Up Your DataCamp Account | 8 | 2018-01-08 06:49 | 1 |  | X |  | Avg Hours Per Day (REMAIN) | 2.3576 | Avg Hours Per Day (CERT) | 1.5488
3.1.2 | Python Data Science Toolbox (Part 1) | 5 | 2018-01-11 08:59 | 2 |  | X
3.1.3 | Data Types for Data Science | 6 | 2018-01-15 02:00 | 2 |  | X |  | Avg Hours Per Week (REMAIN +50%) | 24.7552 | Avg Hours Per Week (CERT+50%) | 16.2628
3.1.4 | Introduction to Data Visualization in Python | 6 | 2018-01-18 19:00 | 3 |  | X |  | Avg Hours Per Day (REMAIN+50%) | 3.5365 | Avg Hours Per Day (CERT+50%) | 2.3233
3.2 | Jupyter Notebook | 1 | 2018-01-19 09:50 | 3 |  | X
3.3 | Git and Github | 2.0833 | 2018-01-20 16:45 | 3 |  | X |  | Customize by changing blue cells
3.4 | Capstone Project Proposal | 1 | 2018-01-21 07:35 | 3 |  | X |  | LEGEND:
4.1.1 | Pandas Foundations | 6 | 2018-01-25 00:35 | 4 |  | X |  | ALL = 100% of course, completed between Start date and Target End Date
4.1.2 | Manipulating DataFrames with Pandas | 6 | 2018-01-28 17:36 | 4 | DUE |  | 6 | REMAIN = 100% of the course, spreading the remaining hours between today and the Target End Date
4.1.3 | Merging DataFrames with Pandas | 6 | 2018-02-01 10:36 | 5 | DUE |  | 6 | CERT = Requirements for the course certificate (100% projects, 60% curriculum) completed between today and Target End Date
4.1.4 | Cleaning Data in Python | 6 | 2018-02-05 03:37 | 5 | DUE |  | 6 | +50% = Springboard recommends allocating 50% additional time to the suggested hours, especially if the topic is new to you
4.2.1 | Python Data Science Toolbox (Part 2) | 6 | 2018-02-08 20:37 | 6 | DUE |  | 6
4.2.2 | Importing Data in Python (Part 1) | 5 | 2018-02-11 22:48 | 6 | DUE |  | 5 | Note - The "Complete by" dates use the ALL method.
4.2.3 | Importing Data in Python (Part 2) | 3 | 2018-02-13 19:18 | 7 | DUE |  | 3
4.2.4 | Work on JSON Based Data Exercises | 1.5 | 2018-02-14 17:33 | 7 | DUE |  | 1.5
4.3.1 | Learn SQL with Mode Analytics | 6 | 2018-02-18 10:33 | 7 | DUE |  | 6
4.3.2 | Analytics Training with Mode Analytics | 4 | 2018-02-20 21:54 | 8 | DUE |  | 4
4.3.3 | Overview of NoSQL Databases | 0.5 | 2018-02-21 05:19 | 8 | DUE |  | 0.5
4.3.4 | Capstone Project - Data Wrangling | 3 | 2018-02-23 01:49 | 8 | DUE |  | 3
5.1.1 | Exploratory Data Analysis | 2 | 2018-02-24 07:29 | 8 | DUE |  | 2
5.1.2 | Storytelling and Effective Communication | 2 | 2018-02-25 13:09 | 8 | DUE |  | 2
5.1.3 | Effective Presentations | 2 | 2018-02-26 18:49 | 8 | SOON |  | 2
5.2 | Work on Your Data Story | 10 | 2018-03-04 23:10 | 9
6.1.1 | Statistical Thinking in Python (Part 1) | 5 | 2018-03-08 01:21 | 10
6.1.2 | Statistical Thinking in Python (Part 2) | 6 | 2018-03-11 18:21 | 10 |  |  |  | Not required for cert
6.2.1 | Human Body Temperature Using EDA | 1.5 | 2018-03-12 16:36 | 10 |  |  |  | Not required for cert
6.2.2 | Examine Racial Discrimination Using EDA | 1 | 2018-03-13 07:26 | 11 |  |  |  | Not required for cert
6.2.3 | Reduce Hospital Readmissions Using EDA | 2 | 2018-03-14 13:06 | 11 |  |  |  | Not required for cert
6.3 | A/B Testing | 0.25 | 2018-03-14 16:49 | 11 |  |  |  | Not required for cert
6.4 | Capstone Project - Inferential Statistics | 6 | 2018-03-18 09:49 | 11
7 | Capstone Project - Milestone Report | 10 | 2018-03-24 14:10 | 12
8.1.1 | Bias and Regression | 3 | 2018-03-26 10:40 | 12 |  |  |  | Not required for cert
8.1.2 | Regression (continued) | 3 | 2018-03-28 07:11 | 13 |  |  |  | Not required for cert
8.1.3 | Classification, kNN, Cross-validation, Dim… | 3 | 2018-03-30 03:41 | 13 |  |  |  | Not required for cert
8.1.4 | Supervised Learning with Scikit-Learn | 6 | 2018-04-02 20:41 | 13 |  |  |  | Not required for cert
8.1.5 | Linear Regression Using Boston Housing | 3 | 2018-04-04 17:11 | 14 |  |  |  | Not required for cert
8.1.6 | Heights and Weights Using Logistic Regr… | 2 | 2018-04-05 22:52 | 14 |  |  |  | Not required for cert
8.2.1 | SVM and Evaluation | 3 | 2018-04-07 19:22 | 14 |  |  |  | Not required for cert
8.2.2 | Decision Trees and Random Forests | 3 | 2018-04-09 15:52 | 14 |  |  |  | Not required for cert
8.3.1 | Bayes Theorem and Bayesian Methods | 3 | 2018-04-11 12:22 | 15 |  |  |  | Not required for cert
8.3.2 | Predicting Movie Ratings from Reviews .. | 2 | 2018-04-12 18:02 | 15 |  |  |  | Not required for cert
8.4 | Best Practices in Supervised Learning | 3 | 2018-04-14 14:33 | 15 |  |  |  | Not required for cert
8.5.1 | Clustering | 3 | 2018-04-16 11:03 | 15 |  |  |  | Not required for cert
8.5.2 | Unsupervised Learning in Python | 6 | 2018-04-20 04:03 | 16 |  |  |  | Not required for cert
8.5.3 | Customer Segmentation Using Clustering | 2 | 2018-04-21 09:44 | 16 |  |  |  | Not required for cert
9.1 | Capstone Project - Final 1 | 6 | 2018-04-25 02:44 | 17
9.2 | Capstone Project - Final 2 | 6 | 2018-04-28 19:44 | 17
9.3 | Capstone Project - Final 3 | 6 | 2018-05-02 12:45 | 18
9.4 | Capstone Project - Final 4 | 6 | 2018-05-06 05:45 | 18
9.5 | Capstone Project - Final 5 | 6 | 2018-05-09 22:46 | 19
| TOTAL HOURS | 207.0833
| Total Curriculum Hours | 145.5833
| Total Capstone Project Hours | 61.5
| HOURS COMPLETED | 37.3333 | 18.03%
| HOURS REMAINING | 169.75 | 81.97%
| Curriculum Hours Required for Cert (60%) | 87.35
| Capstone Hours Required for Cert (100%) | 61.5
| TOTAL HOURS FOR CERT | 148.85
| HOURS COMPLETED FOR CERT | 37.3333 | 25.08%
| HOURS REMAINING FOR CERT | 111.5167 | 74.92%
Note on C5: says 10 min but actually requires 2 * 4 hour courses in python

## Ref - Springboard plan in Excel
Chapter / Unit | Description | Hours | Complete by (Min) | Week # (Min) | Complete by (Max) | Week # (Max) | Target # of months to complete course: | 4 | Hours Per Week (Min): | 7 | Hours Per Week (Max): | 14 | Start Date: | 2018-01-02
1 | Getting started with Intermediate Data Science: Python | 0.083333 | 2018-01-02 | 1 | 2018-01-02 | 1
2.1 | Demystifying Data Science | 0.66667 | 2018-01-02 16:00 | 1 | 2018-01-02 08:00 | 1
2.2 | Start Thinking About Your Capstone Project | 1.5 | 2018-01-04 04:00 | 1 | 2018-01-03 02:00 | 1
3.1.1 | Set Up Your DataCamp Account | 8 | 2018-01-12 04:00 | 2 | 2018-01-07 02:00 | 1
3.1.2 | Python Data Science Toolbox (Part 1) | 5 | 2018-01-17 04:00 | 3 | 2018-01-09 14:00 | 2
3.1.3 | Data Types for Data Science | 6 | 2018-01-23 04:00 | 4 | 2018-01-12 14:00 | 2
3.1.4 | Introduction to Data Visualization in Python | 6 | 2018-01-29 04:00 | 4 | 2018-01-15 14:00 | 2
3.2 | Jupyter Notebook | 1 | 2018-01-30 04:00 | 5 | 2018-01-16 02:00 | 3
3.3 | Git and Github | 2.0833 | 2018-02-01 06:00 | 5 | 2018-01-17 03:00 | 3
3.4 | Capstone Project Proposal | 1 | 2018-02-02 06:00 | 5 | 2018-01-17 15:00 | 3
4.1.1 | Pandas Foundations | 6 | 2018-02-08 06:00 | 6 | 2018-01-20 15:00 | 3
4.1.2 | Manipulating DataFrames with Pandas | 6 | 2018-02-14 06:00 | 7 | 2018-01-23 15:00 | 4
4.1.3 | Merging DataFrames with Pandas | 6 | 2018-02-20 06:00 | 8 | 2018-01-26 15:00 | 4
4.1.4 | Cleaning Data in Python | 6 | 2018-02-26 06:00 | 8 | 2018-01-29 15:00 | 4
4.2.1 | Python Data Science Toolbox (Part 2) | 6 | 2018-03-04 06:00 | 9 | 2018-02-01 15:00 | 5
4.2.2 | Importing Data in Python (Part 1) | 5 | 2018-03-09 06:00 | 10 | 2018-02-04 03:00 | 5
4.2.3 | Importing Data in Python (Part 2) | 3 | 2018-03-12 06:00 | 10 | 2018-02-05 15:00 | 5
4.2.4 | Work on JSON Based Data Exercies | 1.5 | 2018-03-13 18:00 | 11 | 2018-02-06 09:00 | 6
4.3.1 | Learn SQL with Mode Analytics | 6 | 2018-03-19 18:00 | 11 | 2018-02-09 09:00 | 6
4.3.2 | Analytics Training with Mode Analytics | 4 | 2018-03-23 18:00 | 12 | 2018-02-11 09:00 | 6
4.3.3 | Overview of NoSQL Databases | 0.5 | 2018-03-24 06:00 | 12 | 2018-02-11 15:00 | 6
4.3.4 | Capstone Project - Data Wrangling | 3 | 2018-03-27 06:00 | 13 | 2018-02-13 03:00 | 7
5.1.1 | Exploratory Data Analysis | 2 | 2018-03-29 06:00 | 13 | 2018-02-14 03:00 | 7
5.1.2 | Storytelling and Effective Communication | 2 | 2018-03-31 06:00 | 13 | 2018-02-15 03:00 | 7
5.1.3 | Effective Presentations | 2 | 2018-04-02 06:00 | 13 | 2018-02-16 03:00 | 7
5.2 | Work on Your Data Story | 10 | 2018-04-12 06:00 | 15 | 2018-02-21 03:00 | 8
6.1.1 | Statistical Thinking in Python (Part 1) | 5 | 2018-04-17 06:00 | 16 | 2018-02-23 15:00 | 8
6.1.2 | Statistical Thinking in Python (Part 2) | 6 | 2018-04-23 06:00 | 16 | 2018-02-26 15:00 | 8
6.2.1 | Human Body Temperature Using EDA | 1.5 | 2018-04-24 18:00 | 17 | 2018-02-27 09:00 | 9
6.2.2 | Examine Racial Discrimination Using EDA | 1 | 2018-04-25 18:00 | 17 | 2018-02-27 21:00 | 9
6.2.3 | Reduce Hospital Readmissions Using EDA | 2 | 2018-04-27 18:00 | 17 | 2018-02-28 21:00 | 9
6.3 | A/B Testing | 0.25 | 2018-04-28 | 17 | 2018-03-01 | 9
6.4 | Capstone Project - Inferential Statistics | 6 | 2018-05-04 | 18 | 2018-03-04 | 9
7 | Capstone Project - Milestone Report | 10 | 2018-05-14 | 19 | 2018-03-09 | 10
8.1.1 | Bias and Regression | 3 | 2018-05-17 | 20 | 2018-03-10 12:00 | 10
8.1.2 | Regression (continued) | 3 | 2018-05-20 | 20 | 2018-03-12 | 10
8.1.3 | Classification, kNN, Cross-validation, Dim… | 3 | 2018-05-23 | 21 | 2018-03-13 12:00 | 11
8.1.4 | Supervised Learning with Scikit-Learn | 6 | 2018-05-29 | 22 | 2018-03-16 12:00 | 11
8.1.5 | Linear Regression Using Boston Housing | 3 | 2018-06-01 | 22 | 2018-03-18 | 11
8.1.6 | Heights and Weights Using Logistic Regr… | 2 | 2018-06-03 | 22 | 2018-03-19 | 11
8.2.1 | SVM and Evaluation | 3 | 2018-06-06 | 23 | 2018-03-20 12:00 | 12
8.2.2 | Decision Trees and Random Forests | 3 | 2018-06-09 | 23 | 2018-03-22 | 12
8.3.1 | Bayes Theorem and Bayesian Methods | 3 | 2018-06-12 | 24 | 2018-03-23 12:00 | 12
8.3.2 | Predicting Movie Ratings from Reviews .. | 2 | 2018-06-14 | 24 | 2018-03-24 12:00 | 12
8.4 | Best Practices in Supervised Learning | 3 | 2018-06-17 | 24 | 2018-03-26 | 12
8.5.1 | Clustering | 3 | 2018-06-20 | 25 | 2018-03-27 12:00 | 13
8.5.2 | Unsupervised Learning in Python | 6 | 2018-06-26 | 26 | 2018-03-30 12:00 | 13
8.5.3 | Customer Segmentation Using Clustering | 2 | 2018-06-28 | 26 | 2018-03-31 12:00 | 13
9.1 | Capstone Project - Final 1 | 6 | 2018-07-04 | 27 | 2018-04-03 12:00 | 14
9.2 | Capstone Project - Final 2 | 6 | 2018-07-10 | 28 | 2018-04-06 12:00 | 14
9.3 | Capstone Project - Final 3 | 6 | 2018-07-16 | 28 | 2018-04-09 12:00 | 14
9.4 | Capstone Project - Final 4 | 6 | 2018-07-22 | 29 | 2018-04-12 12:00 | 15
9.5 | Capstone Project - Final 5 | 6 | 2018-07-28 | 30 | 2018-04-15 12:00 | 15
207.0833
Note on N1: Brian Leip: matches springboard
Note on P1: Brian Leip: matches springboard
Note on C5: Brian Leip: says 10 min but actually requires 2 * 4 hour courses in python

## Ref - Springboard Study Plan
Screenshots taken from:
https://www.springboard.com/workshops/data-science-intensive/learn#/study-plan
Dated:
2018-02-01 | 0:52

## Break info
Start Date | 2018-01-02 |  |  |  |  | Orig end of 3 months paid | 2018-04-02
Froze Acct | 2018-02-16 | 46 | days in before stop | 46.94% | 35.94% | With 1 week extended from Chris | 2018-04-09 | 98 | days prepaid
Restarted Acct |  | 52 | days remaining of prepaid |  |  | Orig target end date | 2018-05-09 | 128 | days for target end date
End Date |  | 82 | days remining to orig target end date (extra $500)
Consider restarting when % complete matches % days for target end date or days prepaid
|  | % | Hrs | Section to Complete
% of prepaid days complete |  | 46.94% | 97.2 | 5.2 | Work on Your Data Story
% of target end days complete |  | 35.94% | 74.42 | 4.3.1 | Learn SQL with Mode Analytics | * will need to pay another $500
Note on E2: Brian Leip: prepaid % complete
Note on F2: Brian Leip: days to target end date complete